## COVER SHEET
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP)
State: | EDO STATE
Reporting period: |  | FY 2025
SABER Focal Person: |  |  | KELVIN UWAIBI
Was this plan prepared in consultation with the Private Sector |  |  |  |  | Yes
|  |  | Public Sector | Private Sector
List of contributing entities: |  |  | Ministry of Budget and Economic Planning, Ministry of Finance Ministry of Business, Trade & Cooperatives Ministry of Physical Planning, Urban & Regional Development Ministry of Agriculture and Food Security Ministry of Environment and Sustainability Ministry of Road and Bridges Ministry of Communication and Orientation Ministry of Local Government and Communality Affairs Ministry of Justice/Attorney General Ministry of Public Security and Safety Ministry of Mining and Energy Ministry of Social Development and Gender Issues Ministry of Youth & Humanitarian Affairs Ministry of Digital Economy, Science & Technology Edo State Investment Promotion Office Edo State Board of Internal Revenue Edo State Procurement Agency, Edo State Geographic Information Service Edojobs Edo State Building and Maintenance Agency Edo State Signage Agency Edo State Transport Authority, Edo State Public, Private, Partnership Office Edo State Information Communication Technology Agency Edo State Electricity Regulatory Agency, Edo State Forestry Commission. Edo State Multi-Door Courthouse Edo State Broadcasting Service | a) Benin Chamber of Commerce, Industry, Mines & Agriculture (BENCCIMA) b) Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Edo Licensed Exporters Association e) Chinese Manufacturing Cluster f) PWD Shoe-making Association g)Association, Oil Palm Growers Association of Nigeria (OPGAN)
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  |  |  | 2024-10-16
Please further to proof of private sector consultation, please include for the purpose of the Verification Protocol: (a) summary of private sector consultation, and (b) list of private sector participants invited to the consultation – including name, organization, designation of representative, phone number and email address and other information as may be deemed relevant

## EDSG- BERAP 2025
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) 2025
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDAs | Contributing MDAs/Organization | Budget N | Planned Start Date | Planned End Date | Comments [DELETE THIS COLUMN AFTER UPDATING THE FILE]
1 | Security | To enhance public safety, strengthen law enforcement, promote investor confidence, improve collaboration with the private sector, ensure accountability, engage communities, and reduce security costs for businesses. These efforts aim to foster a secure environment for economic growth. | a. Improve on the dedicated security task force involving representatives from the police, private security firms, local government, and the business community. This task force coordinates security efforts, provide rapid response to threats, and ensure a unified approach to protecting business areas and key infrastructure. b. Implement continuous training programs to enhance security personnel's skills. c. Foster partnerships between security agencies and businesses for resource sharing and intelligence cooperation. d. Set up oversight bodies to monitor security operations and enforce transparency. e. Launch community policing and neighborhood watch programs to involve local residents in crime prevention. f.Mapping of the areas for installation of the surveillance cameras. g. Purchase of the surveillance cameras as mapped h. Engagement of CCTV Technicians i. Installation of the cameras 5 Powering of the infrastructure through Solar panel already installed. j. Continuous upskilling and retooling the community vigilantee network security for efficiency. | Description: Edo State’s security reform aims to enhance public safety, strengthen law enforcement, and foster a secure, business-friendly environment. Key initiatives include creating an Investor Protection Task Force, promoting public-private partnerships, engaging communities, and ensuring accountability to boost investor confidence and economic growth. Key Targets: a. Reduce crime rates, particularly in commercial and industrial areas, by at least 25%. | Ministry of Public Safety and Security, Edo State Information Communication Technology Agency (EDOICTA), ESIPO and PPP. | Edo State Vigilante Network, Ministry of Justice, Ministry of Communication & Orientation, Ministry of Local Government & Chieftaincy Affairs and all other security agencies, EIRS, Nigeria Cassava Grower Association (NCGA), AWEP, Edo Licensed Exporters' Association, Oil Palm Growers Association of Nigeria (OPGAN), National Association of Leather products in Nigeria (NALPAN). Ministry of Finance. | N100,000,000 | Jan. 2025 | Dec. 2025
2 | Energy (Electricity) | a. Collaborate with independent power generating companies to provide constant electricity to additionals 2000 businesses. b. Improve the costing structure and billing systems of these organisations to make electricity affordable. c. Collaborate with more private power companies to provide mini grids and creating different power packages that can help different business at different levels of operation. c. To collaborate with international organisations to create a solution that fits different levels of businesses/ households d. Conduct an electricity audit. | a. The House of Assembly to pass the new electricity 2024 bill into law. The bill currently in its second reading in the House- follow up to ensure the bill is passed. b. Collaboration with the Benin Electricity Distribution Company (BEDC), Ossiomo Power and New Hamphire to provide prepaid meters to 5,000 businesses. c. Meet with 20 new investors to discuss investment in the electricity sector. d. Collaborate with development partners to create an electricity audit for the state. f. Energy sector establishment of solar farm as an alternative energy to power communities at Eyaen, Ohovbe, Aduwawa, Irrua, Oza Community. g. Provide renewable energy infrastructure in hospitals across the 18 LGAs. | a. The Electricity Bill is passed and assented to by Mr. Governor. b. Alternative power solutions that are relatively affordabble such as minigrids, mini power packs for small businesses. c. Increase access to eletricity by 15%. | Ministry of Mining and Energy | a. Electricity Regulatory Agency b. Ministry of Business Trade and Cooperatives c. Ministry of Communication & Orientation d. Board of Technical and Vocational Education e. Genuis HUB, Edo State Exporters Cluster f. JNAPLWD, PWD Shoe-making Association | 100000000 | Jan. 2025 | Dec. 2025
3 | Enhancing Job Creation | a. Ability to create direct and indirect jobs b. Skills acquisition c. Fostering a conducive business environment d. Attracting investment by improving the ease of doing business e. Job Security. | a. Job audit through Surveys, roundtable and stakeholders engagement b. Improve the Edo Jobs portal c. Mentorship and Apprenticeship d. Monitoring factors militating against job creation e. Enabling more job creation f. Support for SMES: Access to finance Training/ capacity building: Fashion Skills, Digital Skills, Vocational and Technical Skills. | a. Reduction of Edo State emploment rate from 19% to 15% b. Provision of additional 10,000 skilled jobs and 25,000 unskilled jobs. | Ministry of Business Trade and Cooperatives, Edojobs, ESIPO, Ministry of Science, Technology & Digital Economy, Ministry of Agricuture and Food Security. Ministry of Finance. | Bank of Industry, Micro finance Institutions, Commercial Banks, N.G.OS, Private Sectors (Small and Medium), Doers Upliftment, Foundation, Agricultural Machineries and Equipment Fabricators, Association of Nigeria (AMEFAN), LAPO MFB, NASME, Phecom Craft World, NAWE. | 1000000000 | Jan. 2025 | Dec. 2025
4 | Infrastructure | a. Creating accessibility b. Efficiency and productivity c. Save time d. Increase profit e. Increase access to raw materials f. Access to market and allows for better trading g. Technical Problems h. Decongestion i. Proximity j. Public trust: Ethnic and better trust by the people k. Disallows for health hazards reducing long hours on the road. | a. Rehabilitation of roads/maintenance b. Building of new and interconnected road c. d. Traffic, Regulation enforcement and checks on overloading e. Building and maintaining alternative roads e.g railway f. Collaboraton of Private Public Partnership g. Create a Committee that comprises of Federal, State, Local Government and Private Sector. h. State wide survey of Road Network for construction to be followed by assigned responsibilities which will be broken to task. | a.Rural Roads and Health Roads- fix a minium of 5 roads in each LGA. b.Inter-State Roads: Follow up with the Federal Government in the fixing of the Benin- Ekpoma-Uromi-Auchi Road. | a. Ministry of Roads and Bridges b. Collaboration between the State and FERMA d. Local Government | FERMA, Talented Women Farmer, BENCIMMA, AWEP, NASME, LAPO, Private sector and Organisations Edo State. | 25000000000 | Jan 2025 | Dec. 2025
5 | Access to Market / Communication | To sell made-in Edo products and servicesof MSMEs to local and international markets. | a.Training/ sensitization of MSMEs practionals on digital marketing skills to sell their products locally and internationally b. To push for a local content policy in ensuring that local products and services are patronised by government and private off-takers c. Modify the Edo State export strategy document d. Provide of guidance on improving product packaging to meet both local and international standards. e. To track the process of certification for locally made product in making sure that more products become certified in line with local and international standards. | a. sensitization / data collection from MSMEs b. 2000 MSMES to be trained on digital skills c. Increase purchase of made in Edo products by 5%. | Edojobs, MBTC, ESIPO, Ministry of Science, Technology & Digital Economy | Ministry of Communication & Orientation, NACCIMA Youth Entrpreneur, Edo State Chapter, Edo State Cooperative Farmers, Coalition of Traders & Artisans in Edo State, Edo Shippers Association and National Association of Small Scale Industralists (NASSI). AFAN, SON, NEPC, FACAN, Exporters cluster, Fedral Ministry of Trade and Investment | 50000000 | Jan. 2025 | Dec. 2025
6 | Improve Transpotation and Logistics | To enhance the efficiency and cost-effectiveness of the transportation and logistics infrastructure in Edo State, reducing the cost and time associated with the movement of goods and services within and outside the state. | a. Development of Edo State Comprehensive Transport Master Plan b. Construction of Stella Obasanjo Hospital Bus Terminals, New Benin, Ramat and Sapele road, as well as across the 18 LGAs. c. Operations and management by Planet Projet Ltd, with the inclusion of transport unions (NURTW, RTEAN). d. E-payment. e. Procurement of two water 30-seater bus as a pilot scheme. f. Free mass movement of Edo state dwellers round the State (Intra and Inter State) g. To procure 100 CNG Buses h. Development and construction of more junctions improvement works. i. Develop regulations on intracity operators, E-hailing, Dispatch/logistics riders. j. Profiling of bus owners/drivers, taxis, Toyota yaris vehicles. k. Issuance of Security Stickers l. Construction of Computerised Vehicle Inspection Centers and Drivers Testing Centers in 18 LGAs under Public Private Partnership (PPP) arrangement. m. Kick off Edo State CNG conversion incentive program for vehicles. | a. Reduce transportation time for goods by at least 20%. b. Lower logistics costs for businesses, especially MSMEs. C. Enhance the safety and security of commuters by 10% | Edo State Transport Authority, MOFI, PPP | Ministry of Budget and Planning, Edo State Board of Internal Revenue, Ministry of Finance, Edo State Procurement Agency, Edo State Building and Maintenance Agency Ministry of Budget and Planning, Ministry of Finance, Edo State Procurement Agency, Ministry of Environment, Edo State Signage Agency, Edo State Electricity Regulatory Agency, Ministry of Physical Planning, Housing and Urban Development | 30000000000 | Jan. 2025 | Dec. 2025
7 | Regulatory Framework and Institutional Reforms | a. Simplify business regulations across sectors, with particular attention to reducing redundant procedures in land acquisition, taxation, and labor laws. b. Address the current economic realities. c. Use policy thrust to support the growth and development of MSMEs in Edo State. | a. Conduct a legislative review of CAP45. Initiate a detailed review of the current bendel state cooperative law to identify outdated provisions and gaps. b. Seek approval of the current Edo State Policy on Micro, Small, and Medium Enterprises (MSMEs) and gazette. c. Establish a comprehensive trade mark policy for the 'Proudly Edo' logo aimed at protecting the intellectual property right associated with the brand, promoting local products and services and ensuring its proper use by businesses and instituitions. | a. Organise consultative meetings with Cooperative members, government agencies and relevant stakeholders. Conduct at least 3 consultative sessions across the 3 senatorial districts in Edo State. b. Collaborate with Ministry of Justice to draft the amendment bill, incorporating feedback from the stakeholders consultations and ensuring the law aligns with current cooperative best practices. Submit amendment bill to the Edo State House of Assembly within a month of commencing the reform process. c. Complete a comprehensive review within the stipulated time, and identify sections for amendment. | MBTC | Ministry of Justice, Edo Cooperative Federation, Registered Cooperative bodies. | 15000000 | Feb. 2025 | Nov. 2025
8 | Commercializing and last-mile expansion of fiber optic access and provision of Free Wifi to drive business development. | The reform aims to commercialize, promote, and establish fiber optic broadband access through local last-mile service providers to stimulate business development within the state and economy growth. Further, Expand the infrastructure to offer free WiFi access in local business districts, fostering connectivity and accessibility for all businesses. | a. Determine the business district that would benefit most from high-speed fiber optic connectivity. b. Conduct surveys and market research to gauge interest and willingness to pay for fiber optic services. c. Evaluate the presence and offerings of existing internet service providers in the target areas. d. Create a detailed financial business plan, including projected revenue, expenses, and return on investment. e. Secure the required permits and licenses from local, state, and federal authorities to construct and operate fiber optic infrastructure. g. Ensure compliance with all relevant regulations and standards, including those related to right-of-way access and network construction. h. Create customized internet packages and services that meet the specific needs of different business sectors. i. Create additional service offerings such as cloud computing, data storage, and cybersecurity solutions for business access at lower rates. j. create awearness across the district. k. Determine the specific business districts where free WiFi access would be most beneficial l. Evaluate the existing internet infrastructure in these areas to identify potential gaps or limitations. m. Consult with the local business community to understand their needs and priorities. n. Install the WiFi access points in the designated locations, ensuring proper coverage and signal strength. o. Set up the network with appropriate security measures, such as encryption and access controls. | a. This would create opportunities for local fibre optic engineers on last-mile deployment and internet broadband retail services to business owners. b. Empower small and medium-sized enterprises to achieve a 50% increase in business growth within the first 2 years c. Improve economic development and job creation by 10% within 1 year. d. Increased and enhance broadband connectivity across the State. e. Effectively expand free WiFi access in local business districts, providing a valuable amenity for residents, visitors, and businesses. f. Achieve 90 % internet accessibility and utilization by the business onwers. | Edo ICTA | Ministry Road & Bridge; ESIPO, | 100000000 | Jan. 2025 | Dec. 2025
9 | Business Information Hub | a. To provide easy access to up-to-date regulatory information b. To improve understanding of business policies and opportunities in Edo State c. To reduce information asymmetry between government and businesses | a. Gather all relevant business-related information, regulations, and policies. b. Develop a web platform to host this information-Develop a centralized online platform providing up-to-date c. information on regulations, policies, and opportunities for businesses in Edo State. d. Implement a robust search functionality e. Create a system for regular updates of the information f. Include interactive guides on navigating regulatory requirements for different industries. g. Launch the hub and promote it to businesses h. Set up a feedback mechanism for continuous improvement | a. A centralized online platform providing comprehensive, up-to-date information on regulations, policies, and opportunities for businesses in Edo State. b. Consolidate information from at least 20 government agencies c. Achieve 10,000 unique monthly visitors within 6 months of launch d. Reduce information-related inquiries to government offices by 40% | Edo ICTA ESIPO, MBTC | BMO (Business Member Organizations) | 100000000 | Jan. 2025 | Dec. 2025
10 | Government-Business Interaction Platform | a. To enhance communication between businesses and government agencies b. To increase accountability and responsiveness in government-business interactions c. To create a trackable system for business inquiries and complaints | a. Identify all key points of interaction between businesses and government agencies b. Design a unified platform for these interactions c. Develop the platform with separate modules for different types of interactions d. Implement a robust ticketing and tracking system e. Train government staff on using the platform f. Conduct a pilot with selected businesses and agencies g. Full rollout across all relevant government departments | A secure portal for businesses to interact with government agencies, submit inquiries, and receive official responses. Reduce average response time to business inquiries from days to 24 hours Achieve a 50% reduction in in-person visits to government offices Attain an 85% resolution rate for submitted inquiries/complaints | Edo State ICTA ESIPO | Office of the Governor, All MDAs and BMO | N/A | Jan. 2025 | Dec. 2025
11 | Digital Skills Training Program | a. To enhance digital literacy among business owners and employees b. To enable businesses to leverage technology for growth and efficiency c. To create a more competitive business environment in Edo State. | a. Assess the digital skill gaps in the local business community b. Develop a curriculum covering essential digital skills c. Create online training modules and resources d. Set up a learning management system to deliver the training f. Gather feedback and refine the curriculum g. Scale up the program to reach more businesses. | a. Online courses and workshops to enhance digital literacy among business owners and employees. b. Train 10,000 business owners and employees in the first year c. Achieve a 40% increase in digital tool adoption among trained businesses d. Attain a 90% satisfaction rate among training participants. | Edo ICTA, ESIPO and Ministry of Digital Science and Economy. | MBTC, Edojobs and BMOs | 90000000 | Jan. 2025 | Dec. 2025
12 | Business Process Automation Tools | a. To improve operational efficiency of businesses, especially SMEs b. To reduce operational costs for businesses c. To promote the adoption of modern business practices. | a. Identify common business processes that can benefit from automation. b. Research and select appropriate automation tools or develop custom solutions c. Set up a platform to provide these tools to businesses d. Develop user guides and training materials e. Launch the initiative with a set of basic tools f. Provide training and support to businesses g. Continuously add new tools based on business needs. | a. Cloud-based tools or partnerships with software providers to help businesses automate their internal processes. b. Onboard 5,000 SMEs to use at least one automation tool in the first Achieve a 30% increase in productivity for businesses using the tools c. Reduce operational costs for participating businesses by an average of 20%. | Edo State ICTA ESIPO, | MBTC, Edojobs and BMOs | 50000000 | Jan. 2025 | Dec. 2025
13 | SME Support portal | a. To provide targeted support for small and medium enterprises b. To facilitate access to resources, mentorship, and funding for SMEs c. To promote the growth and sustainability of the SME sector in Edo State. | a. Identify key support areas for SMEs (e.g., funding, mentorship, training) b. Design a comprehensive support portal c. Develop the portal with separate modules for different types of support d. Partner with relevant organizations (e.g., banks, successful entrepreneurs) e. Populate the portal with initial resources and opportunities f. Launch a pilot with a select group of SMEs g. Gather feedback and continuously improve and expand the offerings. | a. A dedicated online platform for small and medium enterprises (SMEs) offering resources, mentorship connections, and access to funding opportunities. b. Connect 5,000 SMEs with mentors or funding opportunities in the first year c. Increase the survival rate of new SMEs by 30% over 3 years d. Facilitate $10 million in funding for SMEs through portal-initiated connections. | Edo State ICTA, and ESIPO | MBTC, EdoJobs, BMOs and Financial Institutions | 10000000 | Jan. 2025 | Dec. 2025
14 | EDSG digital service hub across the State | To create a Public Service Delivery system that would ensure access to efficient, effective, and citizen/business-centric EDSG services through One-Stop-Shop platforms | a. Construct Digital hubs in strategic locations across the State b. Develop a plan for the automation of all critical government services. c. Digitalized the full operations with an ICT system for the hubs and ICT support services via Omni channel platforms (USSD, mobile numbers portals, etc.) d. Develop the EDSG hud digital service plan e. Strategy to ensure all government common services are on online platforms. | a. The public digital service hub is a one-stop shop for all government services and transactions. The hub provides a platform for Government ministries & Agencies to interact more effectively with citizens and businesses. b. Digitize and automate 80% of critical Government services online. c. Drastically reduces the cost of movement for business especially in rular areas d. Promote inclusiveness and enhanced citizen's convenience and experience. | Edo State ICTA, Building Maintenance Agency and Min. of Road & Bridges | All MDAs | 10000000 | Jan. 2025 | Dec. 2025
15 | Ease access to land and Support agricultural growth through land-intensive initiatives. | To make the process of acquiring land seamless also it will attract more investor into the agricultural sector; thereby improving land governance, provide / enhance equitable access to land. | a. Community engagement and sensitization campaign. b. Draft and introduce land access laws that prioritize equity, sustainability, and economic development c. Adoption of appropriate evaluation design for the reform d. Collect baseline and post-reform data e. Analyze data and measure impact. | Description: In Edo State, Agriculture is a key economic activity. Despite the State's potential a significant amount of land remains underutiliszed due to poor access and land tenure insecurity. Targets: Hence, this reform aims to simplify access to land viz a viz equitable access for individuals (smallholder Farmers), communities, Private Sector and Enterpreneurs, with special emphasis on individual right to their accestrial land. | Ministry of Agriculture and Food Security. ESIPO, Ministry Finance | Edo State Forestry Commission and EDOGIS. | 100000000 | Jan. 2025 | Dec. 2025
16 | Operationalization of the State Government Special Purpose Vehicle: Edo State Solid Mineral Mining and Investment Company Limited | To establish and operationalize the Edo State Solid Mineral Mining and Investment Company Limited as a Special Purpose Vehicle (SPV) to promote sustainable development and investment in the state's solid mineral sector. | a. Finalize and implement the legal and regulatory framework governing the operations of the SPV. This includes ensuring compliance with national mining laws and developing state-specific regulations that encourage investment while protecting the environment and local communities. b. Secure initial capitalization for the SPV c. Conduct comprehensive geological surveys andmapping of the state's solid mineral resources d. Engagement with Mining Investors e. Registration and acquisition of 100 mineral title/licences for investment purposes. f. Identification of Economic Minerals in the State. g. Investors engagement h. Liaising with Mining Cadastre Office for Mineral Title. | Description: To provide a platform for Edo State Government to partner with investors in the Mining Sector Key Targets: a. Attract at least $100 million in investments from local and foreign mining companies by the end of 2025. b. Complete geological mapping of at least 70% of the state’s identified solid mineral reserves by mid-2025 and make data available to potential investors. c. Launch at least one large-scale mining operations in partnership with private sector investors by Q4 2025, with the SPV fully operational. | Ministry of Mining and Energy | Ministry of Justice, Ministry of Business, Trade and Cooperatives and ESIPO. | N100,000,000 | Jan. 2025 | Dec. 2025
17 | Grievance Redress Mechanism- Mediation Center Digitalisation | a. Streamline Case Management: Implement a digital case management system to track and manage all mediation cases, allowing for faster and more organized workflows. b. Expand Remote Access: Enable online submission of cases, document sharing, and virtual mediation sessions, allowing users to resolve disputes without needing to visit the MDC physically. c. Enhance Efficiency: Reduce manual processes by automating routine tasks such as scheduling, notifications, and follow-ups, thereby increasing overall efficiency. d. Ensure Data Security: Implement secure digital systems to protect sensitive information, ensuring confidentiality and data integrity for all parties involved in mediation. | a. Develop a Digital Case Management System. b. Create an Online Portal for Users. c. Digitize Records and Documentation. d. Automate Scheduling and Notifications. e. Provide Training for Staff and Mediators. f. Ensure Data Security and Compliance. g. Monitor and Evaluate System Performance. | Description: The Mediation Center Digitalization aims to transform how mediation services are delivered at the Multi-Door Courthouse by integrating technology into every aspect of case management and communication, ultimately improving efficiency and expanding access to mediation services. Key Targets: a. Digitize 90% of mediation case records within the first year of implementation. b. Ensure that 80% of mediation requests are submitted online by the end of the second year. c. Conduct 50% of mediation sessions virtually by 2025, particularly focusing on users from rural areas. d. Reduce case processing times by 30% through automation and efficient digital workflows. | Edo State Multi-Door Courthouse (ESMDC) and Edo State Information Communication Technology Agency (ICTA). | Edo State Investment Promotion Office (ESIPO) and German Agency for International Cooperation (GIZ) | 16,000,000
18 | ODR Training Programs | a. Enhance Skills for Digital Mediation and Arbitration: Train professionals on the use of technology and best practices for conducting ODR sessions. b. Expand Access to ODR Services: Equip mediators with the tools to offer virtual services, ensuring greater accessibility for users who cannot attend in-person sessions. c. Expand Access to ODR Services: Equip mediators with the tools to offer virtual services, ensuring greater accessibility for users who cannot attend in-person sessions. d. Prepare for Future Innovations: Stay ahead of technological advancements by training staff in emerging ODR technologies such as AI-based tools, digital case management systems, and virtual reality (VR) for dispute simulations | a. Develop ODR Training Curriculum: b. Partner with Technology Providers: c. Conduct Regular Training Workshops: d. Certify Mediators in ODR: e. Implement Continuous Learning Programs: f. Promote ODR Services to the Public: | Description: This action area focuses on building the capacity of MDC mediators and staff to effectively handle online disputes, thereby extending the reach of mediation and arbitration services beyond physical locations. Key Targets: a. Train and certify 80% of MDC mediators in ODR within the first year. b. Conduct 100 ODR sessions by the end of the second year. c. Establish partnerships with at least two technology providers for ODR training and support. d. Reduce the need for in-person dispute resolution by 50% in rural areas through the use of ODR by 2025. | Edo State Multi-Door Courthouse (ESMDC) | Edo State Investment Promotion Office (ESIPO), German Agency for International Cooperation (GIZ), Mediation Training Institute Nigeria (MTI-Nigeria) and Institute of Chartered Mediators and Conciliators (ICMC). | 2,000,000 | Feb. 2025 | Dec. 2025
19 | Public Awareness and Education Campaigns | a. Increase Public Knowledge of ADR Services: Educate individuals, businesses, and communities on the availability and advantages of ADR methods provided by the MDC. b. Encourage Early Dispute Resolution: Promote the use of mediation and other ADR methods as a first step before escalating disputes to litigation, saving time and costs. c. Enhance Public Confidence in ADR: Build trust in ADR methods and demonstrate their effectiveness through real-life examples and success stories. d. Reach Underserved Communities: Ensure that rural, low-income, and marginalized groups are informed about ADR options and how to access them. | a. Develop a Multi-Channel Awareness Campaign: b. Host Community Outreach Programs: Leverage Social Media and Digital Platforms: c. Engage Business and Professional Groups d. Collaborate with Educational Institutions e. Promote Success Stories f. Provide Resources in Multiple Languages | Description: This action area focuses on increasing awareness of alternative dispute resolution methods among the general public, businesses, and underserved communities. It emphasizes the cost-effectiveness, efficiency, and amicable outcomes that ADR can offer. Key Targets: a. Increase public awareness of ADR services by 50% within two years, as measured by surveys and website traffic analytics. b. Conduct 100 public workshops or seminars on ADR by 2025, with at least 30% taking place in rural or underserved areas. c. Achieve a 25% increase in the number of cases resolved through ADR methods at the MDC within two years. d. Distribute at least 20,000 educational materials (pamphlets, videos, digital content) by the end of 2025. | Edo State Multi-Door Courthouse (ESMDC), Edo State Information Communication Technology Agency (ICTA) and Edo State Broadcasting Service (EBS) TV % Radio. | Edo State Investment Promotion Office (ESIPO), Indepentent Television and Radio (ITV Benin),Mediation Training Institute Nigeria (MTI-Nigeria), Institute of Chartered Mediators and Conciliators (ICMC) and The Nigerian Bar Association (NBA). | 8000000 | Feb. 2025 | Dec. 2025
20 | Accessibility to information and transparency of government processes | This reform area will assess the level of investment promotion, the quality and availability of state information, and its structures provided to businesses and investors. Further, buiding on the gains from 2023-2024. | i. Assess whether there have been reforms increasing access to information by the government. ii. Examine how robust has this framework been to capture reform progress? iii. Measures private sector knowledge of state information network. What are the official state communication lines and is the public aware of them? iv. Evaluate the efforts that are being made to sensitize public awareness of MDA services that affect businesses? v. Assess the kind of information from state structures whether it boosts private sector confidence or weakens it? vi. Develop a strategy for investors’ messaging using all her communication lines. vii. Assess how quickly economic initiatives are communicated to the public daily especially initiatives bothering on security, investment, trade, agriculture, tax, land, environment, education, health, justice etc. taken by relevant MDAs. viii. Assess the communications team’s relationship with implementing MDAs whether it provides support on the communication of reforms to different stakeholder groups. ix. Engage in aggressive promotional campaigns through newsletters and all communication lines available to sensitize public awareness of reforms progress on a regular basis. | The target is the private sector and the general public. The second part of the reform assesses how the state uses its information services to disseminate information of value to the business community. Investment starts with information and knowing what the government is doing in terms of provision of public goods will enable the public take advantage of opportunities that ultimately stimulate commercial activities. | Edo State Investment Promotion Office, Ministry of Finance | Edo State Internal Revenue Service, Ministry of Agriculture & Food Security, Ministry of Local Government & Chieftaincy Affairs, Ministry of Environment & Sustainability, Ministry of Mining & Energy, Ministry of Business, Trade & Cooperatives, Ministry of Physical Planning, Housing & Urban Development, Ministry of Health, Ministry of Education, Ministry of Communication & Orientation, Ministry of Water Resources, Ministry of Arts, Culture & Tourism, Edo State Multi-Door Courthouse, Small Claims Court, Edo State Geographic Information Service, Edo State Health Insurance Commission, Edo City Transport Service, Edo State Waste Management Board, Edo State Judiciary etc. | 100000000 | 2025-01-25 | 2025-12-24
21 | Tax Harmonization | Harmonize taxes and levies across local government areas to reduce the tax burden on businesses and eliminate multiple taxation. | Stakeholder Consultation: Organize meetings with relevant stakeholders, including local government authorities, private sector associations, and the tax authorities. a. Draft Harmonized Tax Policy- Develop a policy framework that aligns all applicable taxes and levies across LGAs with state and federal policies. b. Legislative Review- Engage the state House of Assembly to review and enact the harmonized tax policy into law. c. Public Sensitization- Carry out campaigns to inform businesses about the new tax structure and compliance processes. d. Tax Database Integration- Implement a unified tax collection system across local governments to centralize tax administration and eliminate overlaps. | a. To reduce tax-related disputes by 25% by the end of 2025. b. Full adoption of the harmonized tax policy across all LGAs in Edo State by mid-2025. | Edo State Ministry of Finance | Edo State Internal Revenue Service (EIRS) Local Government Councils Ministry of Local Government and Chieftaincy Affairs, MBTC, ESIPO, FIRS | N100,000,000 | 2025-01-01 | 2025-12-01
22 | Tax Credit Scheme | Scale up the implementation of the Tax Credit Scheme to attract more private sector investment in infrastructure projects across Edo State. | a. Broaden the scope of infrastructure projects eligible for the scheme to include more sectors such as renewable energy, healthcare, and technology. b. Organize more frequent consultations with large companies and multinationals to increase their participation in the scheme. c. Simplify the application and approval process to make it more attractive for companies to apply. d. Strengthen the monitoring and evaluation mechanisms to ensure accountability and timely completion of projects. e. Review the tax credit percentages and incentives to attract more investments and maximize the impact of the scheme. | Increase private sector participation by 30% and secure at least 10 new infrastructure projects under the scheme by 2025. | Ministry of Finance | Edo State Internal Revenue Service (EIRS) Ministry of Roads and Bridges Edo State Investment Promotion Office (ESIPO) Ministry of Health (for healthcare projects) | N200,000,000 | 2025-01-01 | 2025-12-01
23 | Esan Enterprise Park | Establish the Esan Enterprise Park as a major industrial and manufacturing hub in Edo State to drive economic growth, attract investment, and create jobs in the region. | a. Finalize and implement the plan for the development of the 400-hectare Esan Enterprise Park. b. Begin construction of key infrastructure, including roads, water supply, power, and digital connectivity to attract investors. c. Launch targeted campaigns to attract local and foreign investors, focusing on sectors such as manufacturing, agribusiness, and technology. d. Ensure all necessary regulatory approvals and environmental impact assessments are completed in a timely manner. e. Foster partnerships with private sector companies to co-develop parts of the park and provide essential services. f. Establish vocational training centers within the park to equip the local workforce with the skills required by industries operating in the park. | Achieve 15% completion of infrastructure development in the park by 2025. Secure investments from at least 5 companies by 2025, creating 2,000 direct jobs and 5,000 indirect jobs. | Edo State Ministry of Business, Trade, and Cooperatives. | Edo State Investment Promotion Office (ESIPO), Ministry of Roads and Bridges, Ministry of Environment and Suitainability Edo State Skills Development Agency | N500,000,000 | 2025-01-01 | 2025-12-01
24 | Interstate Trade | Facilitate interstate trade within the BRACED states and position Edo State as a gateway for AfCFTA opportunities. | a. Trade Facilitation Forum- Organize an annual BRACED Trade Forum to promote collaboration and synergy among member states. b. AfCFTA Awareness Campaign- Implement campaigns to educate businesses on AfCFTA trade protocols, benefits, and compliance requirements. c. Infrastructure Improvement- Enhance road networks, logistics hubs, and digital trade platforms for seamless interstate trade. d. Policy Review- Align state trade policies with the AfCFTA protocols to reduce non-tariff barriers and simplify trade processes. e. Trade Partnerships- Develop strategic partnerships with logistics providers and other stakeholders to improve the ease of goods movement across BRACED states and AfCFTA signatories. f. Trade Facilitation Support- Provide technical and financial support to MSMEs in the state for compliance with interstate and AfCFTA trade standards. | Increase trade volume between Edo and other BRACED states by 25% by 2025. Facilitate 100 new export-ready MSMEs from Edo State to take advantage of AfCFTA by mid-2025. | Ministry of Business Trade and Cooperatives. | Edojobs, ESIPO, Ministry of Roads and Bridges, Ministry of Agricuture and Food Security, Ministry of Finance, Benin Chamber of Commerce, Industry, Mines and Agriculture (BENCCIMA). | N500,000,000 | 2025-01-25 | 2025-12-01