## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP)
State: | EDO STATE
Reporting period: |  | FY 2024
SABER Focal Person: |  |  | KELVIN UWAIBI
Was this plan prepared in consultation with the Private Sector |  |  |  | Yes
List of contributing entities: |  |  | a) Benin chamber of commerce industry mines & agriculture (BENCCIMA) b) Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Edo Licensed Exporters Association e) Atiode Solar Energy f) CCETC Ossiomo Power Company g) Speed FM Radio Station h) Reverso Business Service Limited i) KiteGEN Research j) KiteGEN Research
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  |  | 2023-12-20
Please further to proof of private sector consultation, please include for the purpose of the Verification Protocol: (a) summary of private sector consultation, and (b) list of private sector participants invited to the consultation – including name, organization, designation of representative, phone number and email address and other information as may be deemed relevant

## BERAP
EDO STATE BUSINESS ENABLING REFORM ACTION PLAN (BERAP) 2024
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | List of Private Sector contributors | Estimated costs (N) | Planned Start Date | Planned End Date
1 | Quick determination of commercial disputes | To streamline and expedite the resolution process for business-related conflicts. | (i) Conduct quarterly surveys and interviews with businesses and legal professionals to identify specific pain points in the current dispute resolution process. (ii) Introduce legislation that enforces the use of alternative dispute resolution methods before litigation. (iii) Establish 4 more Small Claims Court across the state with judges specializing in commercial law matters. (iv) Build capacity of magistrates on Commercial Dispute Resolution to handle specific types of disputes. (v) Implement a digital case management system at the small claims court that allows parties to file documents online and track the progress of their cases in real-time. (vi) Introduce an online platform for e-filing and electronic submission of evidence at small claims court & multi-door courthouse. (vii) Develop a virtual courtroom system for remote hearings at the small claims court. (viii) Introduce a mandatory pre-action mediation or settlement conference before filing a lawsuit in the Edo State Judicial process. (ix) Provide guidelines for exchanging information and attempts at settlement before formal proceedings. (x) Offer reduced filing fees for cases submitted to arbitration or mediation at the multi-door courthouse (xi) Establish a panel of trained mediators and arbitrators to facilitate ADR processes. (xii) Collaborate with legal education institutions to offer specialized courses in commercial dispute resolution. (xiii) Implement a fast-track process for cases involving a specific monetary threshold. Set strict timelines for the completion of certain stages, such as pre-trial conferences and discovery. (xiv) Introduce a fee-shifting rule, where the losing party bears the legal costs of the prevailing party. (xv) Penalize parties for filing frivolous or meritless claims by imposing cost sanctions. (xvi) Launch a public information campaign through media channels, explaining the benefits and procedures of the reformed dispute resolution system. (xvii) Develop informational materials, such as brochures and online resources, to educate businesses and individuals. (xviii) Establish a performance evaluation committee to regularly assess the efficiency and effectiveness of the new system. (xix) Collect feedback from stakeholders through surveys and public consultations and set-up a special response team at the secretariat to assist with business challenges with government. (xx) Seek input from international experts in commercial dispute resolution to incorporate global best practices. | (i) Description: Conduct a comprehensive review of the current commercial dispute resolution processes, including case timelines, procedural steps, and key stakeholders. Key Targets: Identify bottlenecks and areas of delay in the current system. Analyze the effectiveness of existing mechanisms in resolving disputes. (ii) Description: Amend existing legislation to incorporate provisions that expedite the resolution of commercial disputes and encourage alternative dispute resolution methods. Key Targets: Introduce a timeline for the resolution of commercial cases. Enforce mandatory pre-action mediation or settlement conferences. (iii) Description: Establish dedicated courts or tribunals with judges specializing in commercial law to handle specific types of disputes. Key Targets: Create a separate docket for commercial cases. Appoint judges with expertise in commercial law. (iv) Description: Implement a digital case management system to streamline the filing and tracking of commercial disputes. Key Targets: Develop an online platform for e-filing and document submission. Ensure real-time tracking of case progress. (v) Description: Introduce technology-driven solutions, such as online filing and virtual courtrooms, to enhance the efficiency of the dispute resolution process. Key Targets: Establish a virtual courtroom system for remote hearings. Provide training on digital tools for legal professionals. (vi) Description: Develop pre-action protocols requiring parties to engage in early settlement discussions before initiating formal litigation. Key Targets: Establish guidelines for pre-action mediation or settlement conferences. Encourage parties to exchange relevant information before filing a lawsuit. (vii) Description: Encourage the use of ADR methods by providing incentives and establishing a panel of trained mediators and arbitrators. Key Targets: Offer reduced filing fees for cases submitted to arbitration or mediation. Establish a pool of qualified ADR professionals. (viii) Description: Conduct training programs for judges, lawyers, and court staff to enhance expertise in commercial law and dispute resolution techniques. Key Targets: Develop workshops on the latest developments in commercial law. Collaborate with legal education institutions for specialized courses to train judges. (ix) Description: Implement fast-track procedures for cases meeting specific criteria, with strict timelines for key stages of the legal process. Key Targets: Define criteria for cases eligible for fast-track procedures. Set timelines for pre-trial conferences, discovery, and hearings. (x) Description: Introduce mechanisms to manage and control costs, including fee-shifting rules and penalties for frivolous claims. Key Targets: Implement a fee-shifting rule where the losing party bears legal costs. Impose cost sanctions for filing frivolous or meritless claims. (xi) Description: Launch public information campaigns to educate businesses and the public about the benefits and procedures of the reformed dispute resolution system. Key Targets: Create informational materials, such as brochures and online resources. Utilize media channels for awareness campaigns. (xii) Description: Establish mechanisms for ongoing monitoring and evaluation of the reformed system's effectiveness, with regular feedback collection. Key Targets: Form a performance evaluation committee to review monthly activities on Multi-door courthouse. Conduct quarterly surveys and public consultations to obtain feedback from public. (xiii) Description: Establish mechanisms for ongoing monitoring and evaluation of the reformed system's effectiveness, with regular feedback collection. Key Targets: Set-up a performance evaluation committee to review small claims court monthly activities. Conduct quarterly surveys and public consultations to obtain feedback from public on small claims court. | 1) Business member organisations seeking timely resolution of commercial disputes. 2) Legal professionals in Edo State navigating the dispute resolution process. 3) Courts in Edo State Judiciary aiming to streamline case management. 4) ADR professionals in the state gaining opportunities for practice. 5) Judges and legal professionals in Edo State improving their skills. 6) Legal education institutions contributing to professional development. 7) Businesses and individuals gaining awareness of streamlined dispute resolution. 8) The public understanding the importance of efficient legal processes 9) Stakeholders contributing to the improvement of the dispute resolution system. 10) Decision-makers such as State House of Assembly and Public servants adapting policies based on continuous feedback. | (i) Edo State Judiciary (ii) Small Claims Court. (iii) Edo State Multi-Door Court House | Ministry of Justice | a) Benin chamber of commerce industry mines & agriculture (BENCCIMA) b) Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Edo Licensed Exporters Association e) Atiode Solar Energy f) CCETC Ossiomo Power Company g) Speed FM Radio Station h) Reverso Business Service Limited i) KiteGEN Research j) KiteGEN Research | 4 million | 2024-01-08 | 2024-12-31
2 | Improve access to investment and business information for increased investment inflow | The reform objective is to improve the accessibility of essential business information, making the state more appealing to potential investors. The goal is to stimulate economic growth, leverage opportunities across diverse sectors, and establish a business environment characterized by transparency, competitiveness, and support for entrepreneurship. This reform aims to position Edo State as an attractive destination for investments, driving positive economic outcomes and contributing to sustainable development. | (a) Enact and Strengthen Legislation: • Action: Draft, enact, or strengthen laws that mandate transparency and provide access to government information. (b) Establish Information Portals: • Action: Create user-friendly online platforms and information portals. (c) Promote Open Data Initiatives: • Action: Implement open data policies. (d) Train Government Officials: • Action: Conduct training programs for government officials (e) Implement Whistleblower Protection: • Action: Enact or enhance whistleblower protection laws. (f) Enhance Digital Infrastructure: • Action: Invest in digital infrastructure. (g) Develop Communication Strategies: • Action: Create communication plans. (h) Involve Civil Society and Media: • Action: Foster collaboration with civil society and media. (i) Conduct Public Awareness Campaigns: • Action: Launch public awareness campaigns. (j) Establish Oversight Mechanisms: • Action: Create independent oversight bodies. (k) Encourage Public Feedback: • Action: Implement mechanisms for public feedback. (l) Regularly Update Information: • Action: Ensure regular updates of information. (m) Facilitate Access for Persons with Disabilities: • Action: Ensure accessibility for all. (n) Measure and Report Progress: • Action: Establish performance metrics. | 1. Enact and Strengthen Legislation: • Details: Develop clear legal frameworks that define the scope of transparency, outline obligations, and establish penalties for non-compliance. • Key Targets: Draft, enact, or amend at least 1 law related to transparency and access to information. 2. Establish Information Portals: • Details: Centralize information on government activities, budgets, policies, and services, making it easily accessible to the public. • Key Target: Establish and maintain user-friendly information portals. • Upgrade digital infrastructure to support online platforms and communication. 3. Promote Open Data Initiatives: • Details: Release non-sensitive government data in machine-readable formats, encouraging innovation and allowing citizens and businesses to analyze and use the information. • Key Target: Implement open data initiatives by releasing non-sensitive data in machine-readable formats. 4. Train Government Officials: • Details: Educate public servants on the importance of transparency, data disclosure, and proper communication with the public. • Key Target: Provide at least 3 training programs to educate public servants on the importance of transparency, data disclosure, and effective communication. 5. Implement Whistleblower Protection: • Details: Establish mechanisms to protect individuals reporting corruption or malpractice, ensuring confidentiality and preventing retaliation. • Key Target: Establish and enhance whistleblower protection mechanisms, ensuring confidentiality and preventing retaliation. Incentivize whistleblowers’ with money to encourage them to speakup 6. Enhance Digital Infrastructure: • Details: Upgrade technology to support online platforms, e-filing, and electronic communication to streamline information dissemination. Key Targets: Establish and maintain user-friendly information portals. • Upgrade digital infrastructure to support online platforms and communication. 7. Develop Communication Strategies: • Details: Develop strategies to effectively communicate government initiatives, policies, and decisions to the public through various channels, including social media, press releases, and official websites. • Key Targets: Develop communication strategy plan to effectively convey government initiatives, policies, and decisions to the public. 8. Involve Civil Society and Media: • Details: Engage non-governmental organizations, media outlets, and independent watchdogs to monitor government activities and provide checks and balances. • Key Target: Engage in monitoring government activities, advocating for transparency, and providing checks and balances through the EoDB/SABER coordinating unit. 9. Conduct Public Awareness Campaigns: • Details: Educate citizens about their rights to access information, the importance of transparency, and how they can actively participate in governance. Organize 3 roadshows to promote available incentives in Edo State. • Key Target: Monitor and report on government activities, ensuring that information is accessible to the public through Doing Business In Edo TV & Radio program. 10. Establish Oversight Mechanisms: • Details: Establish agencies or commissions responsible for monitoring and ensuring compliance with transparency laws and policies. • Key Target: Monitor and ensure compliance with transparency laws and policies, holding the government accountable through the Ministry of Justice 11. Encourage Public Feedback: • Details: Facilitate channels for citizens to provide feedback on government policies, projects, and services, fostering a more interactive and responsive government. • Key Target: Establish and facilitate channels for citizens to provide feedback on government policies, projects, and services. Set-up customer complaint desk at ESIPO. 12. Regularly Update Information: • Details: Commit to keeping information current and relevant, providing real-time updates on government activities to maintain public trust. • Key Target: Write quarterly newsletters to update public with reform milestones. 13. Facilitate Access for Persons with Disabilities: • Details: Make information accessible to persons with disabilities by providing alternative formats, such as Braille or audio, and ensuring that online platforms comply with accessibility standards. • Key Target: Ensure that information is accessible to persons with disabilities by providing alternative formats and complying with accessibility standards. Add sign language to TV program. 14. Measure and Report Progress: • Details: Define key performance indicators to measure the effectiveness of transparency initiatives and regularly report progress to the public. • Key Target: Assess the effectiveness of transparency initiatives and report on progress in newsletters and TV program. | 1. Citizens: • How they benefit: Citizens gain access to timely, accurate, and comprehensive information about government activities, policies, and services. This empowers them to make informed decisions, hold the government accountable, and actively participate in democratic processes. 2. Government Officials: • How they benefit: Government officials benefit from increased efficiency in communication, streamlined information dissemination, and a more informed and engaged citizenry. Transparent processes also contribute to the credibility and trustworthiness of government institutions. 3. Researchers and Analysts: • How they benefit: Open data initiatives provide researchers and analysts with valuable datasets, fostering innovation, data-driven decision-making, and the development of insights that can contribute to societal progress. 4. Businesses: • How they benefit: Access to transparent information on government policies, regulations, and economic indicators enables businesses to make informed decisions, plan strategically, and participate more effectively in economic activities. 5. Whistleblowers: • How they benefit: Whistleblowers benefit from mechanisms that protect their identity, ensuring confidentiality and preventing retaliation. This protection encourages individuals to report corruption or malpractice without fear of reprisal. 6. Civil Society Organizations: • How they benefit: NGOs and civil society groups benefit from increased access to information, allowing them to monitor government activities, advocate for transparency, and act as watchdogs to ensure accountability. 7. Media Outlets and Journalists: • How they benefit: Media organizations benefit from having access to transparent information, enabling them to report accurately on government activities and hold public officials accountable through investigative journalism. 8. Persons with Disabilities: • How they benefit: Accessible information formats, such as Braille or audio, ensure that persons with disabilities can equally access and understand government information, promoting inclusivity and eliminating barriers. 9. International Collaboration Partners: • How they benefit: Governments engaging in international collaboration benefit from shared best practices, support, and alignment with global standards, contributing to a more harmonized approach to transparency and information accessibility. 10. Educational Institutions: • How they benefit: Educational institutions benefit from access to open data for research purposes, contributing to academic advancement and promoting data literacy among students. 11. Society at Large: • How they benefit: Overall, society benefits from a government that is transparent and provides accessible information. This fosters trust, civic engagement, and a more informed and empowered populace. 12. Innovators and Entrepreneurs: • How they benefit: Open data initiatives provide innovators and entrepreneurs with opportunities to develop applications, services, and solutions that can address societal challenges and contribute to economic growth. 13. Government Officials: • How they benefit: Professionals specializing in government transparency, information management, and communication benefit from enhanced frameworks and systems that facilitate their work and promote best practices. 14. International Organizations and Agencies: • How they benefit: Organizations working on global standards and practices related to transparency benefit from increased collaboration, information sharing, and the alignment of practices across different countries. | 1. Ministry of Justice or Legal Affairs: • Responsible for drafting, enacting, and amending laws related to transparency, access to information, and whistleblower protection. 2. Ministry of Information and Communication: • Oversees communication strategies, public awareness campaigns, and the development of user-friendly information portals. • Ensures that media outlets adhere to ethical standards and transparency in reporting government activities. 3. Ministry of Finance: • Manages budgetary information, financial transparency, and open data initiatives related to economic indicators and government spending. 4. Ministry of Digital Economy, Science and Technology: • Handles the development and maintenance of digital infrastructure, online platforms, and information portals. 5. Office of The Head of Service: • Manages oversight mechanisms, including the establishment of independent bodies or commissions responsible for monitoring compliance with transparency laws. 6. Governor’s Office: • Coordinates international collaboration efforts and engagement with global organizations working on transparency and information accessibility. 7. Ministry of Education or Education Department: • Engages in public awareness campaigns, particularly those aimed at educating citizens about their rights to access information and promoting transparency. 8. Ministry of Social Development and Gender Issues: • Ensures that information is accessible to persons with disabilities by implementing measures like providing alternative formats and complying with accessibility standards. 9. Ministry of Budget Planning and Economic Development: • Collaborates on open data initiatives, providing information relevant to economic policies, regulations, and indicators. 10. Ministry of Business-Trade or Cooperatives: • Collaborates on open data initiatives, providing information relevant to trade policies, business regulations, and investment opportunities. 11. Edo State Investment Promotion Office: • Coordinates with business member organizations, media outlets, and other stakeholders involved in monitoring government activities. 12. John Odigie-Oyegun Public Service Academy: • Develops and implements training programs for public servants on transparency, data disclosure, and effective communication. 13. Auditor General's Office: • Conducts audits and evaluations to assess the effectiveness of transparency initiatives and reports on progress. | Information, Communication-Technology Agency (ICTA). | a) Imalingmhe John Yesufu – Director General Benin chamber of commerce industry mines & agriculture (BENCCIMA) b) Noma Iguisi- Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Nosa Obayuwana- State Coordinator Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Rhone Peters – representative Edo Licensed Exporters Association e) Fred Atiomo- CEO Atiode Solar Energy f) Ekene Francis – staff of CCETC Ossiomo Power Company g) Speed FM Radio Station h) Reverso Business Service Limited i) KiteGEN Research j) KiteGEN Research | 15 million | 2024-01-08 | 2024-12-31
3 | Improve Regulatory Environment for businesses | The objective is to create a more favorable and efficient landscape by simplifying rules, enhancing transparency, and reducing administrative burdens. This involves streamlining processes, making regulations clearer, and promoting fair competition. The goal is to stimulate innovation, attract investment, and foster economic growth by creating a business-friendly climate that balances the needs of businesses with consumer protection. Ultimately, these reforms aim to make it easier for businesses to operate, encouraging entrepreneurship and contributing to overall economic development. | 1. Regulatory Impact Assessment: Conduct a thorough assessment of existing regulations to identify redundancies, inefficiencies, and areas for improvement. This evaluation should consider the economic impact and compliance costs for businesses. 2. Stakeholder Consultation: Engage with businesses, industry experts, and other stakeholders to gather feedback on existing regulations. This collaborative approach ensures that reforms address the actual needs and concerns of those affected. 3. Simplify and Harmonize Regulations: Streamline and simplify regulatory processes to reduce administrative burdens on businesses. Harmonize regulations across different sectors to create a consistent and coherent regulatory framework. 4. Digitalization of Processes: Implement digital solutions to automate and streamline regulatory processes. This can include online application systems, electronic document submissions, and digital communication channels to improve efficiency and reduce paperwork. 5. Transparency Measures: Enhance transparency by making regulatory requirements easily accessible and understandable. Provide clear guidelines and information to businesses regarding compliance procedures and timelines. 6. Training and Capacity Building: Invest in training programs for regulatory agencies to ensure that staff members are well-equipped to implement and enforce regulations effectively. This includes staying informed about industry best practices. 7. Regular Review and Update: Establish mechanisms for regular review and update of regulations to keep pace with changing business landscapes, technology, and market dynamics. This ensures that regulations remain relevant and effective. 8. Risk-Based Regulation: Adopt a risk-based approach to regulation, focusing resources on areas with the highest impact on public interest and safety. This allows for a more targeted and efficient regulatory process. 9. Public-Private Partnerships: Foster collaboration between the public and private sectors to co-create and implement regulatory reforms. This partnership can lead to more practical and business-friendly solutions. 10. Monitoring and Evaluation: Implement a robust system for monitoring and evaluating the effectiveness of regulatory reforms. Regularly assess the impact on businesses, economic growth, and overall regulatory compliance. 11. International Best Practices: Benchmark against international best practices and learn from successful regulatory reforms in other jurisdictions. This can provide valuable insights and guide the implementation of effective regulatory policies. | Description of reform: The reform is a strategic initiative designed to enhance the overall framework governing business activities in the state. It encompasses a systematic review and restructuring of existing regulations with the goal of simplifying processes, promoting transparency, and reducing bureaucratic hurdles. This reform emphasizes the integration of digital solutions to streamline administrative procedures, engagement with stakeholders for constructive feedback, and the adoption of international best practices to inform policy changes. Through this initiative, the aim is to create a conducive and business-friendly environment that encourages entrepreneurship, innovation, and economic development. Key Targets: 1. Simplified Regulations: • Develop a single Demand Notice for the payment of tax across all local government area. • Develop an electronic platform for the collection of taxes, levies, and fees from businesses. • Set-up an automated e-receipt generation QR code or unique payment ID for revenue generating public institutions. • Upgrade the Central Billing System platform to enable revenue generating public institutions receives taxes. • Set-Up 1 State & 1 Local Govt. MSME Councils to address challenges specific to businesses at local government level. • Formulate the Edo State MSME Policy to address pain points of businesses in the Edo State ease of doing business eco system. • Revise the Edo State policy audit document and update it with new reforms and policies. • Reduce time taken to access public goods by 10% from 5 business enabling environment MDAs. • Set-up a State Committee on Export Promotion. • Develop an operational plan for state committee on export promotion. • Formulate an Edo State Export Policy for local businesses. • Register 20 firms in the state with export certificates from Nigerian Export Promotion Council (NEPC). • Increase the number of firms to 40 that obtained export certificates from NEPC since 2021 2. Stakeholder Engagement: • Organize at least one policy dialogue meeting with stakeholders on tax harmonization at local government level. • Organize 1 stakeholders meeting on export policy formulation. 3. Promotional Campaigns: • Promote awareness of MSME support packages in the state through 2 roadshows. • Increase the number of locally made products certified by NAFDAC to 100 in retail stores. • Develop an Export Strategy Plan 4. Capacity Building & International Benchmarking: • Organize 4 training session each quarter to build capacity of public servants on best practices for policymaking. • Introduce a policy formulation process inspired by best practices in Edo State. • Introduce a consultation mechanism with stakeholders in policy formulation. • Build 50 local MSME Capacity on investment readiness through quarterly training sessions. 5. Regular Review and Update: • Organize quarterly information forum with MDAs for regular reviews and updates of regulations to keep them relevant and responsive to evolving business landscapes. 6. Risk-Based Regulation: • Prioritize reforms focusing regulatory efforts on areas with the highest impact on public interest, safety, and fair competition. 7. Monitoring and Evaluation: • Establish KPIs to measure the success of the export strategy plan. | Beneficiaries: 1. Businesses: Reduced regulatory burden, simplified processes, and increased transparency benefit businesses by improving operational efficiency and reducing compliance costs. 2. Entrepreneurs: A more conducive regulatory environment encourages entrepreneurship by providing a supportive framework for starting and growing businesses. 3. Investors: Improved regulatory clarity and a business-friendly environment attract both domestic and foreign investors, fostering economic growth. 4. Consumers: Fair competition and regulatory measures that protect consumer interests contribute to a marketplace that benefits consumers. 5. Economy: The reform aims to stimulate economic growth in the state by creating conditions that facilitate business expansion, job creation, and overall economic development. 6. Edo State Government: Streamlined regulatory processes and a more efficient framework benefit the government by reducing administrative costs, improving compliance, and enhancing the overall effectiveness of regulatory agencies. | 1. Ministry of Business-Trade and Cooperatives 2. Ministry of Local Government and Chieftaincy Affairs 3. All Heads of Local Government Areas (Holgas) 4. Ministry of Finance: 5. Ministry of Justice 6. Edo State Internal Revenue Service 7. Edo State Investment Promotion Office (ESIPO) 8. Edo State Skills Development Agency (EDOJOBS) 9. Ministry of Budget Development and Economic Planning 10. Office of the Head of Service Edo State 11. John Odigie-Oyegun Public Service Academy | a. Department of Bureau of Statistics b. Business Development Support and Export Department-ESIPO c. Edo State Digital Agency | a) Benin chamber of commerce industry mines & agriculture (BENCCIMA) b) Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Edo Licensed Exporters Association e) Atiode Solar Energy f) CCETC Ossiomo Power Company g) Speed FM Radio Station h) Reverso Business Service Limited i) KiteGEN Research j) KiteGEN Research | 10 million | 2024-01-08 | 2024-12-31
4 | Improved efficiency in sustainability of the land-based investment process. | The goal of improving efficiency in the sustainability of land-based investments is to make sure that activities like agriculture and forestry are done in a way that benefits the environment, society, and the economy. This involves using resources wisely, following rules and regulations, adopting technology for better practices, and engaging with local communities. The aim is to create a balance where these investments contribute positively to long-term sustainable development while minimizing negative impacts on the environment and people. | 1. Conduct Comprehensive Assessments: • Conduct thorough environmental, social, and economic assessments to understand the current state and potential impacts of land-based investments. 2. Define Clear Sustainability Standards: • Establish clear and measurable sustainability standards that align with environmental conservation, social responsibility, and economic viability. 3. Develop and Update Regulations: • Strengthen existing regulations or develop new ones to ensure that land-based investments adhere to sustainability standards. Regularly update these regulations to keep pace with evolving best practices. 4. Promote Stakeholder Engagement: • Actively involve local communities, indigenous groups, NGOs, and other stakeholders in decision-making processes. Establish forums for open communication and collaboration. 5. Encourage Technology Adoption: • Incentivize the adoption of sustainable technologies, such as precision farming, agro ecological practices, and efficient irrigation systems, to improve productivity and minimize environmental impact. 6. Provide Training and Capacity Building: • Offer training programs and capacity-building initiatives for farmers, landowners, and relevant stakeholders to enhance their understanding of sustainable practices and technology use. 7. Implement Monitoring and Reporting Systems: • Develop robust monitoring systems to track the environmental, social, and economic performance of land-based investments. Require regular reporting to ensure accountability. 8. Facilitate Access to Finance: • Support access to financing options that prioritize sustainable land-based investments. This can encourage the adoption of environmentally friendly and socially responsible practices. 9. Promote Certifications and Standards: • Encourage the adoption of recognized certifications and standards for sustainable land management, such as organic certifications or sustainable forestry certifications. 10. Establish Land-Use Planning Mechanisms: • Develop and implement land-use planning mechanisms that take into account ecological, social, and economic factors to guide responsible land-based investments. 11. Foster Research and Innovation: • Invest in research and innovation to continually improve sustainable land management practices and identify new technologies and approaches. 12. Create Incentive Programs: • Introduce incentive programs, tax breaks, or subsidies for businesses and individuals who demonstrate a commitment to sustainable land-based practices. 13. Address Social Equity: • Implement measures to ensure fair and equitable distribution of benefits, protect the rights of local communities, and address social equity concerns associated with land-based investments. 14. Establish Grievance Mechanisms: • Develop transparent grievance mechanisms for addressing concerns raised by local communities or other stakeholders. Ensure a fair and accessible process for dispute resolution. 15. Promote Ecosystem Restoration: • Encourage initiatives for ecosystem restoration and rehabilitation, including reforestation programs and sustainable land management projects. 16. Educate and Raise Awareness: • Conduct educational campaigns to raise awareness about the importance of sustainable land management and its positive impact on the environment, society, and the economy. 17. Regularly Review and Adapt Policies: • Periodically review and adapt policies, regulations, and practices based on feedback, monitoring results, and emerging sustainability trends. | The reform seeks to create a responsible and inclusive framework for land-intensive agricultural investment. This framework, known as the Framework for Responsible and Inclusive Land-Intensive Agricultural Investment (FRILIA), serves as a comprehensive guide to minimize the environmental footprint of land-based activities. FRILIA focuses on sustainable practices, efficient resource utilization, social equity, legal compliance, technology adoption, community involvement, risk management, and transparency. Key Targets: 1. Environment: • Clearly define and legally recognize land tenure and rights in regulation or legislation. • Develop and implement FRILIA as a comprehensive framework for responsible land-intensive agricultural investment by Executive Order. 2. Resource Use: • Collaborate with 2 organizations for expertise in sustainability and responsible land use. • Establish a steering committee to implement the FRILIA framework. 3. Social Equity: • Include FRILIA awareness in local TV/Radio programs. • Establish a steering committee for FRILIA with the authority to address social equity concerns and promote inclusive practices. 4. Legal Compliance: • Work with relevant stakeholders to develop clear and comprehensive sustainability guidelines that cover environmental, social, and economic aspects of land-based investments. • Incorporate all four principles of the FRILIA framework applicable to the investment process to enhance legal compliance. 5. Technology Integration: • Develop an online portal where stakeholders, including the public, can access information about ongoing land-based projects, environmental impact assessments, and regulatory compliance. 6. Community Involvement: • Allocate resources to programs enhancing 500 local livelihoods in host communities. • Establish 1 grievance redress mechanism for FRILIA stakeholders to ensure community involvement and address concerns. 7. Risk Management: • Conduct 2 Environmental and Social Impact Assessment before land-based investments. 8. Transparency and Accountability: • Involve local communities and stakeholders in decision-making by conducting 2 policy dialogue sessions.Develop a stakeholders charter to be signed at the project launch. | 1) Local Communities: a. Preserves natural resources b. Protects livelihoods c. Ensures fair distribution of benefits 2) Farmers and Landowners: a. Enhances agricultural productivity b. Optimizes resource use c. Promotes long-term viability 3) Environment: a. Reduces environmental footprint b. Minimizes deforestation, soil degradation, and water pollution 4) Investors and Businesses: a. Ensures long-term success b. Reduces risks c. Promotes profitability through sustainable practices 5) Edo State Government and Regulatory Bodies: a. Supports sustainable development b. Enforces regulations effectively c. Promotes social equity 6) Technology Providers: a. Boosts demand for sustainable technologies 7) NGOs and Advocacy Groups: a. Aligns with goals of environmental conservation and social equity 8) Consumers: a. Supports ethical sourcing b. Promotes responsible production 9) Future Generations: a. Preserves natural resources for the well-being of future generations 10) Global Community: a. Contributes to global efforts in environmental conservation and responsible business practices. | 1. Ministry of Agriculture and Food Security: a. Implements agricultural policies b. Oversees sustainable farming practices and land-use planning 2. Ministry of Environment and Sustainability: a. Ensures compliance with environmental regulations b. Monitors the environmental impact of land-based activities 3. Edo State Forestry Commission: a. Manages and regulates forestry practices b. Promotes sustainable logging and reforestation 4. Ministry of Local Government and Chieftaincy: a. Focuses on rural development policies b. Supports local communities and agricultural development 5. Edo State Geographic Information Service: a. Oversees land tenure and land-use planning b. Manages sustainable natural resource use 6. Ministry of Finance: a. Allocates financial resources for sustainable land-based investments 7. Ministry of Digital Economy, Science and Technology: a. Promotes adoption of innovative technologies in agriculture 8. Ministry of Business-Trade and Cooperatives: a. Ensures adherence to responsible business practices and ethical standards 9. Ministry of Youth and Humanitarian Affairs: a. Integrates sustainable development goals into national policies 10. Ministry of Social Development and Gender Issues: a. Addresses social equity concerns b. Ensures fair distribution of benefits 11. Ministry of Communication and Orientation: a. Facilitates transparent communication about land-based investments | 1. Edo State Investment Promotion Agency 2. Ministry of Justice | a) Benin chamber of commerce industry mines & agriculture (BENCCIMA) b) Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Edo Licensed Exporters Association e) Atiode Solar Energy f) CCETC Ossiomo Power Company g) Speed FM Radio Station h) Reverso Business Service Limited i) KiteGEN Research j) KiteGEN Research | 21 million | 2024-01-08 | 2024-12-31
5 | The "Edo State PPP Governance and Fiscal Responsibility Reform." | The reform objective is to establish a robust and comprehensive framework for Public-Private Partnerships (PPPs) in Edo State, Nigeria, with a focus on fiscal commitment and contingent liability management. This initiative aims to facilitate sustainable development by enacting a PPP Law, establishing a dedicated state office, and implementing key measures to enhance transparency, efficiency, and financial responsibility in PPP projects. The overarching goal is to attract private investments, stimulate economic growth, and manage fiscal commitments effectively while ensuring the successful delivery of infrastructure projects through PPPs. | 1. Establish a Committee for the Drafting of Edo State PPP Law: • Constitute a committee comprising legal experts, policymakers, and relevant stakeholders to draft a comprehensive PPP law tailored to the needs of Edo State. 2. Draft PPP Legal and Institutional Framework: • Develop a detailed legal and institutional framework for PPPs, including guidelines and manuals, to guide the implementation and management of partnerships. 3. Enact the PPP Law: • Present the drafted PPP law for legislative approval, ensuring that it aligns with best practices, legal standards, and the specific developmental needs of Edo State. 4. Establish a Dedicated State Office for PPPs: • Create a specialized state office tasked with overseeing PPP initiatives, managing fiscal commitments, and ensuring adherence to the established legal and institutional framework. 5. Develop the PPP Fiscal Commitment and Contingent Liability Framework (FCCL): • Design a robust fiscal commitment and contingent liability management framework to assess, manage, and mitigate financial risks associated with PPP projects. 6. Implement the PPP Disclosure Framework: • Develop and enforce a PPP disclosure framework to enhance transparency by providing relevant information to the public, potential investors, and stakeholders. 7. Create a Website for Publishing Pipeline PPP Projects: • Establish an online platform to publish information about ongoing and upcoming PPP projects, creating a transparent and accessible repository for interested parties. 8. Set Up a PPP Project Facilitation Fund: • Create a dedicated fund to facilitate PPP projects, providing financial support for feasibility studies, project preparation, and other early-stage activities. 9. Publish Right-of-Way (ROW) Acquisition Process: • Collaborate with relevant Ministries, Departments, and Agencies (MDAs) to publish a clear and comprehensive process for obtaining Right-of-Way (ROW), including associated costs and timelines. 10. Develop a PPP Project Facilitation Fund: • Establish a fund to support the facilitation of PPP projects, providing financial assistance for feasibility studies, project preparation, and initial development stages. 11. Implement the PPP Disclosure Framework: • Enforce the disclosure framework for PPP projects, ensuring transparency by publishing essential project information on the state website. 12. Promote Stakeholder Engagement: • Foster collaboration and communication with stakeholders, including local communities, private investors, and government agencies, to gather input and address concerns. 13. Capacity Building and Training: • Conduct training programs for relevant personnel involved in PPP implementation to enhance their understanding of the legal framework, financial management, and project delivery. 14. Monitoring and Evaluation Mechanism: • Establish a robust monitoring and evaluation mechanism to track the performance and impact of PPP projects, allowing for continuous improvement and accountability. 15. Promote Investment Attraction: • Develop marketing strategies to attract private investments by showcasing the benefits of PPPs, the transparent framework, and the state's commitment to sustainable development. 16. Regular Review and Updating of Frameworks: • Periodically review and update the PPP legal and fiscal frameworks to adapt to changing circumstances, legal standards, and emerging best practices. | Description of the Reform: The reform initiative aims to establish a robust and comprehensive framework for Public-Private Partnerships (PPPs) in Edo State, Nigeria. Focused on fiscal commitment and contingent liability management, the reform involves the enactment of a specialized PPP law, the creation of a dedicated state office, and the implementation of measures to enhance transparency, efficiency, and financial responsibility in PPP projects. Key Targets of the Reform: 1. Enactment of PPP Law: • Draft and pass a PPP law that aligns with best practices, legal standards, and the specific developmental needs of Edo State. 2. Establishment of a Dedicated State Office: • Create a specialized state office responsible for overseeing PPP initiatives, managing fiscal commitments, and ensuring adherence to the established legal and institutional framework. 3. Development of Fiscal Commitment and Contingent Liability Framework (FCCL): • Design and implement a robust FCCL to assess, manage, and mitigate financial risks associated with PPP projects, ensuring fiscal responsibility. 4. Implementation of PPP Disclosure Framework: • Develop and enforce a PPP disclosure framework to enhance transparency by providing relevant information to the public, potential investors, and stakeholders. 5. Creation of a Website for Publishing PPP Projects: • Establish an online platform to publish information about ongoing and upcoming PPP projects, promoting transparency and accessibility. 6. Establishment of a PPP Project Facilitation Fund: • Set up a dedicated fund to facilitate PPP projects, providing financial support for feasibility studies, project preparation, and early-stage activities. 7. Publication of Right-of-Way (ROW) Acquisition Process: • Collaborate with relevant MDAs to publish a clear and comprehensive process for obtaining Right-of-Way, including associated costs and timelines. 8. Promotion of Stakeholder Engagement: • Foster collaboration and communication with stakeholders, including local communities, private investors, and government agencies, to gather input and address concerns. Organize at least one policy dialogue session on the availability of a PPP office in the state. 9. Capacity Building and Training: • Conduct 3 training programs for relevant personnel involved in PPP implementation to enhance their understanding of the legal framework, financial management, and project delivery. 10. Establishment of a Monitoring and Evaluation Mechanism: • Create a robust monitoring and evaluation mechanism to track the performance and impact of PPP projects, allowing for continuous improvement and accountability. Set-up an M & E department in the Edo State PPP Office 11. Promotion of Investment Attraction: • Develop marketing strategies to attract private investments by showcasing the benefits of PPPs, the transparent framework, and the state's commitment to sustainable development. Organize 2 roadshows to promote PPP investment in Edo State. 12. Regular Review and Updating of Frameworks: • Periodically review and update the PPP legal and fiscal frameworks to adapt to changing circumstances, legal standards, and emerging best practices. | i. Government and Public Sector: a. Improved project implementation efficiency b. Access to private sector expertise ii. Private Sector: a. Increased investment opportunities b. Business growth potential c. Clearer frameworks for engagement in PPPs iii. Local Communities: a. Improved infrastructure b. Enhanced public services c. Potential economic growth and job creation iv. Civil Society Organizations: a. Increased transparency and accountability b. Improved community engagement v. Investment and Financial Institutions: a. Increased opportunities for project financing vi. Project Implementers and Developers: a. Streamlined process for initiating and delivering PPP projects vii. Public Service Consumers: a. Improved and efficient public services viii. Government Employees: a. Capacity-building opportunities b. Potential job opportunities associated with PPP projects ix. Economic Development Agencies: a. Tools to attract private investments b. Stimulate economic growth x. Environmental and Social Organizations: a. Potential inclusion of sustainable practices in PPP projects b. Addressing social needs and contributing to community well-being xi. Educational and Research Institutions: a. Opportunities for research collaboration and knowledge transfer related to PPPs. | 1. State House of Assembly: • Responsible for passing the specialized PPP law to establish the legal framework for PPPs. 2. Office of the Governor: • Provides overall leadership and support for the reform initiative. 3. Edo State PPP Office: • The dedicated office responsible for overseeing PPP initiatives, managing fiscal commitments, and ensuring adherence to the established legal and institutional framework. 4. Committee for the Drafting of Edo State PPP Law: • Comprising legal experts, policymakers, and stakeholders, responsible for drafting the PPP law. 5. Ministry of Roads and Bridges: • Responsible for publishing the process for obtaining Right-of-Way, including relevant MDAs' timeframe and cost. • Involved in infrastructure development and may collaborate with other relevant ministries on Right-of-Way processes. 6. Ministry of Finance: • Involved in the development of the fiscal commitment and contingent liability management framework, as well as promoting investment attraction. 7. State MSME Council: • Involved in advocating for the interests of public service consumers. 8. Strategy, Policy, Projects and Performance Management Office (SPPPMO): • Responsible for establishing a robust monitoring and evaluation mechanism for tracking PPP project performance. 9. Ministry of Environment and Sustainability: • Ensures compliance with environmental and social standards in PPP projects. 10. Ministry of Justice: • Ensures that PPP projects adhere to legal standards and regulations. 11. Edo State Investment Promotion Office: • Involved in promoting investment opportunities and fostering a conducive business environment. | I. Edo State Transport Authority II. Electricity Regulatory Commission III. Edo State Information Communication Technology Agency | a) Benin chamber of commerce industry mines & agriculture (BENCCIMA) b) Edo State Chapter Chairman Nigerian Association of Small Scale Industrialists (NASSI) c) Sustainable and Inclusive Economic Development For Decent Employment in Nigeria-GIZ-SEDIN Programme d) Edo Licensed Exporters Association e) Atiode Solar Energy f) CCETC Ossiomo Power Company g) Speed FM Radio Station h) Reverso Business Service Limited i) KiteGEN Research j) KiteGEN Research | 10 million | 2024-01-08 | 2024-12-31
| BERAP ACTIVITIES TOTAL BUDGET ESTIMATED COST | [7 empty] | 60 million
Key
Delete
Good
Update Required

## BERAP implementation guide
S/N | Reform Area | Actions | Accountable MDA (Initiative Level) | MDA champions/ responsible individuals | Planned Start date | Planned End date | Status | Date Completed | EBES involvement level | Comment
Monitoring and Evaluation by EBES
Monitoring and Evaluation by EBES
Monitoring and Evaluation by EBES
Direction by EBES
Monitoring and Evaluation by EBES
Direction by EBES
Monitoring and Evaluation by EBES
Direction by EBES
Monitoring and Evaluation by EBES
Monitoring and Evaluation by EBES
Monitoring and Evaluation by EBES

## Progress Report (hidden)
BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
| The focus area for the reforms eg transparency of official fees and procedures | What the State intends to achieve by implementing the Business Enabling Reform | Very detailed, step by step process on how the objective will be achieved | User, beneficiaries, recipient of the reform Explain actions and/or sub-actions and include targets | One MDA responsible for the action/activity | Supporting MDAs | Estimated budget for the action/activity | When you commit to start the implementation of the actions | When you commit to complete the actions and achieve tour targets | Indicate whether the action/activity is completed, ongoing - on time, ongoing - delayed or dropped | Describe the status of each action, explaining reasons for any delays or actions being dropped. Explain any changes that occurred during implementation affecting start and end dates | Describe next steps for the outstanding actions. For example, is the action getting carried over to the following year's action plan?
1 | Illustrative example: Transparency of official fees and procedures | Illustrative example: This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs | Illustrative example A. Finalise process mapping of one business regulatory area number 1 | A description of the action and target, e.g. business regulatory process mapping signed off by all included MDAs and approved by the relevant authority | List the one MDA that would be responsible for this action/activity | List the several MDAs that would actively contribute to the activity | Amount (in Naira) | Day, Month, Year | Day, Month, Year
Illustrative example A.1. Map existing process for carrying out impact evaluation
B.
B.1
B.2
C.
C.1
C.2